## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Green
Sollute
Estoque Certo
Data do Inicio do Projeto (Sprint 2): | 2022-03-12 | [10 empty] | Scrolling increment: | [5 empty] | 0
Milestone marker: | 1 | 1 |  |  | março | [20 empty] | abril
[5 empty] | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14
Milestone description | Assigned to | Progress | Start | Days | s | d | s | t | q | q | s | s | d | s | t | q | q | s | s | d | s | t | q | q | s | s | d | s | t | q | q | s | s | d | s | t | q | q
Pesquisa e Inovação
Desenvolver o site em REACT |  | 100% | 2022-03-12 | 36
Criar o PB e SB |  | 100% | 2022-03-22 | 15
Atualizar o DER |  | 100% | 2022-03-20 | 13
Atualizar a documentação |  | 100% | 2022-04-02 | 4
Atualizar GitHub |  | 100% | 2022-03-24 | 9
Engenharia de Software
Protótipos de tela do figma |  | 100% | 2022-03-20 | 13
Interface WEB |  | 100% | 2022-03-23 | 14
Diagrama de solução de software |  | 100% | 2022-03-17 | 10
Planilha de arquitetura |  | 100% | 2022-03-27 | 5
Estrutura de Dados de Armazenamento
Documento de Layout |  | 100% | 2022-03-22 | 8
Atualizar o UML |  | 100% | 2022-03-27 | 8
Usar Classe Java ListaObj |  | 100% | 2022-04-05 | 15
Utilizar Observer, Adapter ou Iterator no código |  | 100% | 2022-03-24 | 13
Técnicas de Prog. WEB
Login e Logoff com ORM |  | 100% | 2022-03-23 | 15
Criar 2 CRUDS com SPRINGBOOT, ORM e JPA |  | 100% | 2022-03-18 | 15
Fazer a persistência de dados no Azure/MySQL utilizando ORM e JPA |  | 100% | 2022-03-12 | 10
Entrega da Sprint 2 |  | 100% | 2022-04-21 | 1
To add more data, Insert new rows ABOVE this one

## Blue
Project title
Company name
Project lead
Project start date: | 2022-04-18 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | maio | [34 empty] | junho
 | time axis 2022-05-01 to 2022-06-25
Milestone description | Assigned to | Progress | Start | Days | time axis 2022-05-01 to 2022-06-25
Title 1
Task 1 |  | 25% | 2022-04-21 | 3
Task 2 |  |  | 2022-04-26 | 1
Task 3 |  | 50% | 2022-04-18 | 10
Task 4 |  |  | 2022-05-11 | 1 | bar: 2022-05-11
Task 5 |  | 10% | 2022-04-27 | 6
Title 2
Task 1 |  | 60% | 2022-04-27 | 13
Task 2 |  | 50% | 2022-04-28 | 9
Task 3 |  | 33% | 2022-05-06 | 11
Task 4 |  |  | 2022-05-15 | 1 | bar: 2022-05-15
Task 5 |  |  | 2022-05-16 | 24
Title 3
Task 1 |  |  | 2022-05-06 | 4
Task 2 |  |  | 2022-05-10 | 14
Task 3 |  |  | 2022-05-26 | 6
Task 4 |  |  | 2022-06-08 | 3
Task 5 |  |  | 2022-05-31 | 19
Title 4
Task 1 |  |  | 2022-05-28 | 15
Task 2 |  |  | 2022-05-20 | 5
Task 3 |  |  | 2022-07-10 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Purple
Project title
Company name
Project lead
Project start date: | 2022-04-18 | [10 empty] | Scrolling increment: | [5 empty] | 13
Milestone marker: | 1 | 1 |  |  | maio | [34 empty] | junho
 | time axis 2022-05-01 to 2022-06-25
Milestone description | Assigned to | Progress | Start | Days | time axis 2022-05-01 to 2022-06-25
Title 1
Task 1 |  | 25% | 2022-04-21 | 3
Task 2 |  |  | 2022-04-26 | 1
Task 3 |  | 50% | 2022-04-18 | 10
Task 4 |  |  | 2022-05-11 | 1 | bar: 2022-05-11
Task 5 |  | 10% | 2022-04-27 | 6
Title 2
Task 1 |  | 60% | 2022-04-27 | 13
Task 2 |  | 50% | 2022-04-28 | 9
Task 3 |  | 33% | 2022-05-06 | 11
Task 4 |  |  | 2022-05-15 | 1 | bar: 2022-05-15
Task 5 |  |  | 2022-05-16 | 24
Title 3
Task 1 |  |  | 2022-05-06 | 4
Task 2 |  |  | 2022-05-10 | 14
Task 3 |  |  | 2022-05-26 | 6
Task 4 |  |  | 2022-06-08 | 3
Task 5 |  |  | 2022-05-31 | 19
Title 4
Task 1 |  |  | 2022-05-28 | 15
Task 2 |  |  | 2022-05-20 | 5
Task 3 |  |  | 2022-07-10 | 5
Task 4
Task 5
To add more data, Insert new rows ABOVE this one